# Phase 4: Project Planning – Banquet Hall Booking CRM

## 4.1 Introduction

The Project Planning Phase structures the development process into manageable sprints, assigns responsibilities, sets timelines, and defines milestones. This ensures the team stays aligned and delivers the Banquet Hall Booking CRM on schedule.

## 4.2 Project Timeline & Sprint Plan

### 4.2.1 Overall Timeline

Project Start Date: April 7, 2026

Project End Date: May 16, 2026

Total Duration: 6 Weeks (5 Sprints + 1 Buffer)

Sprint Duration: 1 Week each

### 4.2.2 Sprint Breakdown

#### Sprint 1: Data Modeling (Week 1: Apr 7 – Apr 11)

| Task ID | Task | Assigned To | Estimated Hours | Status |
| --- | --- | --- | --- | --- |
| T-101 | Create Banquet_Hall__c object with all fields | Admin | 4 | Planned |
| T-102 | Create Booking__c object with all fields | Admin | 4 | Planned |
| T-103 | Create Billing__c object with all fields | Admin | 4 | Planned |
| T-104 | Define Lookup relationships between objects | Admin | 2 | Planned |
| T-105 | Create Formula fields (Total Days, Total Amount, Grand Total, Balance Due) | Admin | 3 | Planned |
| T-106 | Create Picklist values for all picklist fields | Admin | 2 | Planned |
| T-107 | Configure Auto-Number fields (Booking Number, Invoice Number) | Admin | 1 | Planned |
| T-108 | Review and validate data model | Business Analyst | 2 | Planned |
|  | Sprint 1 Total |  | 22 hours |  |

#### Sprint 2: User Interface Configuration (Week 2: Apr 14 – Apr 18)

| Task ID | Task | Assigned To | Estimated Hours | Status |
| --- | --- | --- | --- | --- |
| T-201 | Create Lightning App "Banquet Booking Manager" | Admin | 2 | Planned |
| T-202 | Create Custom Tabs for all three objects | Admin | 1 | Planned |
| T-203 | Design Page Layout for Banquet_Hall__c | Admin | 3 | Planned |
| T-204 | Design Page Layout for Booking__c (Celebration Record Type) | Admin | 3 | Planned |
| T-205 | Design Page Layout for Booking__c (Corporate Record Type) | Admin | 3 | Planned |
| T-206 | Design Page Layout for Billing__c | Admin | 3 | Planned |
| T-207 | Create Record Types for Booking__c | Admin | 2 | Planned |
| T-208 | Configure List Views for all objects | Admin | 2 | Planned |
| T-209 | Set up Compact Layouts and Highlights Panel | Admin | 2 | Planned |
| T-210 | UI Review with stakeholders | Business Analyst | 2 | Planned |
|  | Sprint 2 Total |  | 23 hours |  |

#### Sprint 3: Automation & Business Logic (Week 3: Apr 21 – Apr 25)

| Task ID | Task | Assigned To | Estimated Hours | Status |
| --- | --- | --- | --- | --- |
| T-301 | Create Validation Rule: Prevent_Past_Date_Booking | Admin | 1 | Planned |
| T-302 | Create Validation Rule: End_Date_Before_Start | Admin | 1 | Planned |
| T-303 | Create Validation Rule: Guest_Count_Exceeds_Capacity | Admin | 1 | Planned |
| T-304 | Build Flow: Prevent Duplicate Booking (Record-Triggered) | Admin | 4 | Planned |
| T-305 | Develop Apex Trigger: BookingTrigger (Auto-Generate Billing) | Developer | 6 | Planned |
| T-306 | Write Apex Test Class for BookingTrigger (75%+ coverage) | Developer | 4 | Planned |
| T-307 | Test all validation rules with sample data | QA Lead | 3 | Planned |
| T-308 | Test Flow with duplicate booking scenarios | QA Lead | 3 | Planned |
| T-309 | Test Trigger with confirmed/tentative bookings | QA Lead | 3 | Planned |
|  | Sprint 3 Total |  | 26 hours |  |

#### Sprint 4: Reports & Dashboards (Week 4: Apr 28 – May 2)

| Task ID | Task | Assigned To | Estimated Hours | Status |
| --- | --- | --- | --- | --- |
| T-401 | Create Report: Bookings by Event Type | Admin | 2 | Planned |
| T-402 | Create Report: Monthly Revenue Breakdown | Admin | 2 | Planned |
| T-403 | Create Report: Hall Utilization Rate | Admin | 3 | Planned |
| T-404 | Create Report: Pending Payments | Admin | 2 | Planned |
| T-405 | Create Report: Bookings by Status | Admin | 2 | Planned |
| T-406 | Build Dashboard: "Banquet Booking Overview" | Admin | 4 | Planned |
| T-407 | Add Dashboard Components (Pie, Bar, Line Charts) | Admin | 3 | Planned |
| T-408 | Review Reports and Dashboards with Owner | Business Analyst | 2 | Planned |
|  | Sprint 4 Total |  | 20 hours |  |

#### Sprint 5: Testing & Deployment (Week 5: May 5 – May 9)

| Task ID | Task | Assigned To | Estimated Hours | Status |
| --- | --- | --- | --- | --- |
| T-501 | End-to-end functional testing | QA Lead | 6 | Planned |
| T-502 | User Acceptance Testing (UAT) with business users | QA Lead + BA | 4 | Planned |
| T-503 | Bug fixes and refinements | Developer + Admin | 4 | Planned |
| T-504 | Prepare Change Set for deployment | Admin | 2 | Planned |
| T-505 | Deploy to Production org | Admin | 2 | Planned |
| T-506 | Post-deployment validation | QA Lead | 2 | Planned |
| T-507 | Prepare user training materials | Business Analyst | 3 | Planned |
| T-508 | Conduct user training session | Business Analyst | 3 | Planned |
|  | Sprint 5 Total |  | 26 hours |  |

### 4.2.3 Buffer Week (Week 6: May 12 – May 16)

Reserved for final bug fixes, documentation finalization, and demo preparation.

## 4.3 Team Roles & Responsibilities

| Role | Team Member | Key Responsibilities |
| --- | --- | --- |
| Project Manager | TBD | Overall coordination, timeline management, stakeholder communication |
| Business Analyst | TBD | Requirements gathering, UAT coordination, training |
| Salesforce Admin | TBD | Object creation, UI configuration, reports, dashboards, validation rules, flows |
| Salesforce Developer | TBD | Apex Triggers, test classes, complex automation |
| QA Lead | TBD | Test planning, execution, bug reporting |

## 4.4 Risk Assessment

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-001 | Scope creep from additional feature requests | Medium | High | Strict change management process; defer to Phase 2 |
| R-002 | Data model changes mid-sprint | Low | High | Thorough review in Sprint 1; freeze data model after approval |
| R-003 | Apex test coverage below 75% | Medium | Medium | Allocate dedicated time for test class development |
| R-004 | User resistance to new system | Low | Medium | Early stakeholder engagement; thorough training |
| R-005 | Deployment failures | Low | High | Test in sandbox first; use validation-only deployment before actual deploy |

## 4.5 Communication Plan

| Event | Frequency | Participants | Mode |
| --- | --- | --- | --- |
| Daily Standup | Daily (15 min) | All team members | Virtual (Teams/Meet) |
| Sprint Planning | Weekly (Monday) | All team members | Virtual |
| Sprint Review | Weekly (Friday) | All team + stakeholders | Virtual |
| Stakeholder Update | Bi-weekly | PM + Stakeholders | Email + Meeting |

## 4.6 Conclusion

The Project Planning Phase ensures a structured, time-bound approach to building the Banquet Hall Booking CRM. With clear sprint goals, assigned responsibilities, and risk mitigation strategies, the team is prepared for efficient execution in the Development Phase.